## Sheet1
LLM-Driven Verification of Video Content Credibility
Description | September Block1 ( September 2025 - November 2025) | [7 empty] | September Block2 ( November 2025 - January 2025)
| Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8
Proposal Phase
Finalize Project Proposal | bar: September Block1 ( September 2025 - November 2025) Week1 to September Block1 ( September 2025 - November 2025) Week4
Project Proposal Presentation | bar: September Block1 ( September 2025 - November 2025) Week5
Optimise Project Proposal | bar: September Block1 ( September 2025 - November 2025) Week6 to September Block1 ( September 2025 - November 2025) Week7
Submission of Project Proposal | bar: September Block1 ( September 2025 - November 2025) Week8
ImplementationPhase
Project Planning & Preparation | bar: September Block2 ( November 2025 - January 2025) Week1
System Development | bar: September Block2 ( November 2025 - January 2025) Week2 to September Block2 ( November 2025 - January 2025) Week3
System Testing | bar: September Block2 ( November 2025 - January 2025) Week4
System Optimizing | bar: September Block2 ( November 2025 - January 2025) Week5 to September Block2 ( November 2025 - January 2025) Week6
Project Report Documentation | bar: September Block2 ( November 2025 - January 2025) Week7
System Demonstration | bar: September Block2 ( November 2025 - January 2025) Week7
Submission of Final Projec Report | bar: September Block2 ( November 2025 - January 2025) Week8
Progress
Deadline